## Slide 1
ITER
Where are we?
Carlos Alejaldre
Deputy Director-General
ITER Organization

## Slide 2
Summary
The ITER Project
Worksite progress
Manufacturing milestones
Transport & Delivery
A « Basic nuclear installation »
Safety functions
Licensing process
Highlights 2014
Management assessment
Transition
Summary

## Slide 3
R=6.2 m, a=2.0 m, Ip=15 MA, BT=5.3 T, M=23,000 tons
The ITER Project
Demonstrating the availability and integration of the science, technologies and safety features for a fusion reactor
A necessary step on the way towards a commercial fusion reactor
Q ≥ 10
  50 MW in/ 500 MW out
Equal sharing of intellectual property between the seven ITER Members

## Slide 4
PF Coils Building
ITER HQ
Subcontractors Area
Tokamak Pit
Assembly Hall
400 kV switchyard
Cryostat Workshop
The 42-hectare ITER platform is located 35 km to the north of Aix-en-Provence, France.
HQ Extension
Storage Area 2
Storage Area 3
The ITER platform in 2014
Storage Area 1

## Slide 5
Resting on the 493 columns of the paraseismic system, the Tokamak Complex basemat will support the Tokamak Complex buildings. Concrete pouring was finalized on 27 Aug. 2014
The Tokamak Complex basemat
Worksite milestones
Notes: La topographie de la dalle (basemat) du Hall d’Assemblage est plus complexe que celle du Tokamak Pit.
La dalle est également, à certains endroits, beaucoup plus épaisse pour faire place à des galeries et pénétrations.
La densité du ferraillage (rebar) est très forte (1 500 tonnes d’acier dans le béton)
Elle supportera les charges très lourdes des éléments et de l’outillage (tooling) d’assemblage.

## Slide 6
Worksite milestones
The basement-level walls
Work on the first level walls of the Tokamak Complex began in November. It is expected to last until mid-2015.

## Slide 7
Worksite milestones
The Assembly Hall
The pillars for the metallic structure of the Assembly Hall building are being assembled (Nov 2014)

## Slide 8
The Cryostat Workshop
Worksite milestones
Completed in February, the Cryostat Workshop (110 metres long, 44 metres wide and 27 meters tall) was inaugurated in November. Welding and assembly operations for the Cryostat should begin in 2015.

## Slide 9
Manufacturing milestones
Who manufactures what?
Toroidal Field Coils (18)
Poloidal Field Coils(6)
Cryostat
Thermal Shield
Vacuum Vessel
Blanket
Feeders (31)
Divertor
Central Solenoid (6)
Correction Coils(18)
Cooling water system
Only the main components are represented on this slide
Internal coils

## Slide 10
Manufacturing: a few examples
China
13 contracts were placed in this year (one more will be awarded soon. Up to now, 65 contracts have been awarded.
26 main suppliers, more subcontractors and Chinese industries are involved in the ITER project.
The machining of the Coil Terminal Box was completed in April 2014. The Box is now under integral test in ASIPP (Institute of Plasma Physics, CAS) factory
Following mockup development, manufacturing of the first of 18 Correction Coils will be done at the Institute of Plasma Physics, Chinese Academy of Sciences (ASIPP) in Hefei, China.

## Slide 11
Europe
The manufacturing of the first of the 70 radial plates that will support the superconducting cables of ITER’s Toroidal Field coils has started in Italy and France.
Europe is responsible for delivering the 39 buildings of the ITER installation.
Like all ITER Members, it also procures components for the ITER tokamak.
Europe’s contribution represents ~ 45% or the total value of ITER.
Europe has completed its 20.2 percent share of niobium-tin strand production for ITER's toroidal field coils—some 97 tons of material produced by two European suppliers.
Manufacturing… a few examples

## Slide 12
India
In-wall shielding, cryostat, Component Cooling Water System (CCWS), Chilled Water System (CHWS), cryolines, etc. have entered the manufacturing phase.
The on-site Cryostat Workshop was completed in February and inaugurated in November 2014.
In Hazira, India, Larsen & Toubro Ltd workers gather for a picture as the first longitudinal seam of the cryostat base section is readied for “submerged arc welding”.
​Manufacturing is underway in India for the acceleration grid power supplies that will be supplied to ITER's diagnostic neutral beam.
Manufacturing… a few examples

## Slide 13
Japan
First manufactured Central Solenoid conductor (length :620m) at NSSE in Kitakyushu, Japan.
First 5 conductors shipped on 25 June to the US.
Tests completed for power supply for ITER Neutral Beam Test Facility
Manufacturing and testing of the 5 High Voltage bushing rings is ongoing
Upon the completion of jacketing, 760-metre-long toroidal field conductor unit lengths are spooled to facilitate transportation.
At JASTEC’s Moji factory, workers prepare 40- to 100-kg niobium-tin “billets” that will eventually be transformed into millimetre-thin strands.
Manufacturing… a few examples

## Slide 14
Korea
Manufacturing of 27 Toroidal Field conductors (20.18 %) is now completed. Last shipment to Japan in November.
Manufacturing of Vacuum vessel segments and ports is ongoing at Hyundai Heavy Industries.
The ITER Vacuum Vessel is being manufactured at the Hyundai Heavy Industries shipyard in Ulsan, Korea.
Thermal shield prototype fabrication has begun at SFA Engineering Corp.
Manufacturing… a few examples

## Slide 15
Russia
Manufacturing in ongoing for TF Conductors, Upper Ports, Blanket First Wall, Dome divertor, EC gyrotrons, etc.
The last batch of Russian-produced superconducting strands for the ITER magnet system was shipped for cabling on 3 December.
In the last six years, the Chepetsk Mechanical Plant has manufactured ~100 tons of niobium-tin (Nb3Sn) strand for ITER's toroidal field conductor and 125 tons of niobium-titanium (NbTi) strand for the poloidal field conductor.
A prototype of the toroidal field busbars that will feed power to ITER's 18 toroidal field superconducting magnet coils has been successfully manufactured.
Manufacturing… a few examples

## Slide 16
USA
Once de-spooled, the conductor passes to the winding station which forms the conductor into a spiral-wound coil composed of "pancake" layers.
The US ITER Project Office has begun fabrication of the magnet modules with vendor General Atomics. Six superconducting modules for the central solenoid plus a spare will be produced.
Manufacturing of Drain Tank # 1 completed.
Manufacturing of 800m dummy and 100m active Toroidal Field conductor delivered to EU.
A guide tube selector test unit for the pellet injection system is undergoing testing. The unit will support pellet type and pellet position flexibility.
Manufacturing… a few examples

## Slide 17
Transport and delivery
Successful tests
The ITER Itinerary test convoy, featuring an 800-metric-ton trailer replicating the weight and dimensions of ITER’s most exceptional loads, has successfully completed two full tests in September 2013 and April 2014.
The first heavy loads (from USA) are expected in early 2015.
The 104-kilometre long ITER Itinerary, from the Mediterranean to the ITER site
Large-scale public works were carried out by France along the 104 kilometres of the ITER Itinerary in preparation for the exceptional size and weight of some of the ITER components.

## Slide 18
A “Basic Nuclear Installation”
But also because of:
Activated products -tokamak
Activated products -cooling systems
  In addition ITER will produce
Operational and dismantling waste
  Tritiated waste
  Activated waste
  Tritiated and activated waste
Mainly because of a Tritium inventory > 27 g

## Slide 19
Licensing process
Authorisation for INB Creation
Decree
Public Enquiry
Acceptance (MSNR)
Submission of DAC files
March 2010
14 December 2010
23 May 2011
9 September 2011
15 June – 4 Aug 2011
Advice from Enquiry Commission
Advice from CLI-July 2011
2012
Submission to CLI Working Group
Public Enquiry files
Transmission to Environmental Authority
January 2011
Advice from Environmental Authority
13 January 2011
23 March 2011
Prefectoral Order for Public Enquiry
30 November 2011
CLI advice
Examination of RPrS by “Groupe Permanent”
Draft Technical Prescriptions by ASN

## Slide 20
Licensing process
An essential milestone in the history of our Project
A historical achievement for the Fusion development
On 10 November 2012, the Official Journal of the French Republic published the Decree authorizing the International ITER Organization to create the basic Nuclear Installation named ITER at Saint-Paul-lez-Durance. (Bouches-du-Rhône).

## Slide 21
Two Safety Functions
  1- Confinement of radioactive materials
  2 - Limitation of radiation exposure
No safety function are associated to:
Control of the fusion reactions.
Power dissipation (cooling systems)

## Slide 22
Highlights 2014
EU Commission Pdt J-M Barroso: "Europe is proud to believe in ITER"
11 July 2014

## Slide 23
Highlights 2014
US delivers 1st plant components
4 Sept 2014

## Slide 24
Management assessment
As required under the ITER Agreement, an independent management assessment of the ITER Organization (IO) is conducted every two years.
The recommendations of the 2013 Management Assessment were accepted by the ITER Council and IO, and an improvement action plan with detailed actions, indicators and timelines covering the specific areas highlighted in the MA Report, was proposed by the IO and approved by the ITER Council in February/ March 2014
The MA Action Plan is under full-scale implementation, and two follow-up reports on implementation status have been submitted to the IC in June and November 2014
Major ongoing improvement actions
  Extensive improvements in the area of design integration and systems engineering, including recruitment of necessary resources
  Close collaboration between IO and DAs in developing an updated long-term schedule for the IC’s consideration by June 2015, and also in implementing mechanisms for joint decision-making
  Clear focus on improving nuclear safety culture (evidenced by release of B2 slab hold point and completion of concrete pouring) and project culture
  Improved performance for decision process
  Generation of substantial cost savings, to be used for meeting identified cost risks and contingencies

## Slide 25
Transition
On 20 November, the ITER Council nominated Bernard Bigot, from France, presently the Adminsitrator -General of CEA, to succeed Osamu Motojima as the next Director-General of the ITER Organization.

## Slide 26
Thank you
for your attention
Procurement Arrangements already signed with Domestic Agencies representing 90% of the total value of the Project
Construction and components manufacturing in the Members’ industry is well advanced and progressing
Nuclear License under French regulation is obtained
Management Assessment recommendations are implemented
Updated Long Term Schedule will be presented in June 2015 by new Director General
Summary